## Sheet1
Description	Task		Hours
Self Learn
	SDL			<<< passing on SDL
	Develope class/theme framework (config/parent class)				Low level overkill
	Individual Basic funtionality		200		literally will need to code each event class
		touchpad	???		Better if have cash to burn and want 100% revamp
		hover	???
		click	???
		pop ups	???

	color theme style		12
		text/background
		font
		shapes

	Demo

PyQT				<<< framework of choice		many exsisting classes + modal control
	Basic funtionality/feel			21		Just need to hack/customize
	written as Qtouchevent classes	touchpad	3			works with Qtouch + well documented
		hover	3
		click	3
		pop ups	3
		tabs	3
		numpad	6		<< used thoughout, want to make sure it's done right

	Develope class/theme framework (config/parent class)			15
	figure out how to set a global theme setting	text/background	6
		font	3
		shapes	6

	Demo	Basic / feedback wtih eric		4
		look/feel
Prototype
	Develope class/theme framework (config/parent class)
	Individual Widgets	Implement all items but unorganized
	SIGNAL GENERATOR MODE			15
	control	output freq	3		<< 1.5 for both enerty + units
		output power	3
		RF ON.OFF	3

	displays	freq	2		<< check/display units?
		power	2
		on/off	2

	DETECTOR MODE			17
	control_static
		some defaults?	ask eric
	control_sweep
		start/stop freq range	3
		number of steps	3
		RF output power	3

	displays	plot_static	4
		plot_sweep	4

	CONFIG/SETTINGS MODE			7
	control	input_textboxes	4
		check, enable github update button.	3

	Placement/adjustments	organize/back forth		20	I'll go with 20 since it's back and forth, continual
					Also amost certain numpad and static sweep are not fully accounted for here.

			Total ideal	99
			Hourly	40
			Total	3960